## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Laptop malfunction | Laptop is unusable | Low | High | Developer (myself) | Use another machine | Mitigation - Regular pushes to GitHub
COVID-19 infection | Reduced capacity for work | Low | Medium | Developer (myself) | Rest, vitamin C/D, no alcohol | Mitigation - Get booster jab
Integration testing issues | Cannot perform integration tests | High | Medium | Developer (myself) | Find information on subject | Mitigation - Go through content on QA community
DAOTesting malfunction | No connection to MySQL | High | Low | Template Author | Create new database geared for testing | Acceptance - Confront issue if and when it arises
Git misuse | Pushing to Feature branch | Low | Low | Developer (myself) | Merge dev and feature branches in cloned repo then push to forked version | Mitigation - Self educate on Git best practice